## Action Plan: School from IB PYP Evaluation Report November 2007

Please note for confidentiality purposes the word “School” replaces the name of the school, the word “Country” replaces the name of the country the school is in, the “XXX” replaces the city.

| Section A: Philosophy |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal | Strategies | Date to be achieved | Person/group responsible for achieving the goal | Evidence of achievement of, or progress towards, the goal |
| Standard A1 There is close alignment between the educational beliefs and values of the school and those of the programme. |  |  |  |  |
| •Further development of the qualities, attitudes and characteristics described in the Learner Profile in the students. | - Guide students to consistently evaluate and develop descriptors for the articulation of the learner profile in different areas – e.g. in ITC, in the classroom, in respect to the environment and sustainability, at home etc. - Ongoing visiting of the Learner Profile and PYP Attitudes with all school staff (apart from academic staff) to ensure that the international perspectives of the IB are understood throughout the school. Deliver training and workshops in Country for support staff. - In the planning process, develop specific descriptors of the Learner Profiles relevant to each UOI. - Continued parent information and training to support them to extend the characteristics of the IB student into family life beyond school. | 2008/09 and ongoing 2008 (initiated) and ongoing 2008/009 ongoing 2008/009 ongoing | PYP Team and all staff Co-ordinating P and Principals PYP Team and all teachers PYP Co-ord and Principals | Students can articulate what actions they should demonstrate when modelling (for example) a Thinker when they are in classroom setting as opposed to being a Thinker at home or a Thinker when making choices about the future and the environment etc. Students become more internationally minded through the daily application of the Leaner Profile. Support personnel within the broader school understand the values of the programme and can support the students and the teachers to genuinely ‘live’ the mission of the B on a daily basis. In summary – the whole school community are informed, actively model and can describe the Learner Profile as it impacts on their lives and the lives of others. As a result the IB mission is ‘lived’ throughout the school community. |
| • Further development of student critical thinking skills by expanding the program to include more global issues. | - Ongoing staff training during weekly sessions on the importance of critical thinking in 21st century education. - Checklists to ensure that that key questions provoke critical thinking skills. - Develop higher order thinking skills with the use of ‘trigger’ questions. (Ensure questions always challenge by posing ‘who’ what’ ‘when ‘ what if’ etc provocations). - Guide parents to question children to think critically beyond school. Provide them with a framework for questioning via training and written support. - Consistent re-evaluation of each UOI to incorporate significant global issues. | 2008/09 2008/009 ongoing 2008/009 ongoing 2008/009 ongoing 2008/009 ongoing | Leadership Team PYP Team Designated staff “ “ PYP Co-ords Team Leaders | Teachers and parents are able to identify and model ways to lead individual students to develop and use thinking critical skills to actively support their learning both at school and beyond leading them to become 21st Century learners who are able to take responsibility for their ongoing learning. |
| Standards A 2 The school promotes international-mindedness on the part of the adults and the students in the school community. |  |  |  |  |
| • Further exploration and usage of the diverse cultures and perspectives that exist in the school. | - Integrate local, national and global communities (resources) in special events - Further develop and maintain an accurate data base of community resources that enable students to further explore diverse cultural perspectives from within Country that can be accessed within XXX and XXXXX. - Seek opportunities to have teacher /student exchanges outside Country - Expand the teleconference programme to include more international school settings. - Use of technology e.g. Think.com to link students to others with different cultural perspectives. - Establishment of class web pages and sharing these with other schools. - With the establishment of the new Performing Arts Theatre, enable students to regularly experience performances from others and to share personal cultural performances in a professional setting. | 2008/009 ongoing 2009/10 2009/10 2008/009 ongoing 2008/009 ongoing 2009/10 | Admin PYP Team Librarian Team Leaders Administration Team PYP Co-coordinators ITC Team Board, Director Admin Leadership Team | All members of the school community are able to articulate their own culture and share and value this. Students are prepared to take their place in the 21st Century with open minds and global outlooks. Students have contact with and access to a range of people with diverse cultural perspectives. Teachers experience education in another setting to enable them to draw comparisons and share their perspectives. All members of the community have a venue to present, share to explore and share cultural performances. |
| • Exploration of, leading to an understanding of human commonalities through the examination of diverse issues extending beyond the local context. | - Incorporate the IB theme in the overall direction that the whole school will follow each year thereby linking S.C to other IB schools, the raising the international focus of all programs and to ensure that this school is a part of the globally shared IB direction. - Further review of the POI to ensure that it explores human commonalities (significantly the Country cultural diversity) and global issues as they need to be addressed in the 21st Century to lead to racial/ religious tolerance and world peace. - Provide access to resources (via international and local media) that support the issues e.g. establish a big screen at canteen that shows world news during break times. - Promote annual school events to highlight local and global human issues. Ensure that all designated ‘special days’ e.g. Earth Day, United Nations Day etc are marked in advance on all school calendars so that they can be acknowledged within the programme. - Development of transdisciplinary skills that will enable students to connect life at school with life at home and the world. - Access to international journals and readings – subscriptions to National Geographic for Kids online etc. - Environmental Guardianship: - Establishing the school as a ‘green school’ based on the standards and practices of the ‘eco’ hotels and resorts. -Use of guest speakers and NGOs to transform the thinking of the school community -Involvement of parents in the programme so that it may be taken to their residential communities, -Sharing with local schools and surrounding villages. | 2008/009 evaluated annually 2008/009 ongoing 2009/10 2008/009 and expanded annually 2008/009 ongoing 2008/009 ongoing 2008/009 ongoing | Administration Team PYP Team EDP, school wide administration Team Properties Team Country Principals Admin Team , Student Council, PYP Team Properties and leaning/gardening teams Admin + parents Parent Support Group, Admin, Student Council Principals, Student Council | A greater understanding of international perspective and global awareness is enhanced across the school and embraced by all members of the school community. The POI provides scope, through a range of units to explore issues that relate to human tolerance and diversity nationally and internationally and students are aware of and actively pursuing means to explore and discover and take action on issues. School becomes an exemplar model of an environmentally ‘safe and sustainable’ setting. The practices set in place at school are taken to different facets of the XXXX Community to support ongoing sustainability. |
| • Removal of the “English only” zones in the school buildings. *** Matter to be Addressed – see attached information and further details of action taken. | - Remove the signs and information. - Maintain the existing school philosophy which ensures that everyone is culturally accepting of all and continue to value the mother tongue of all who enter the school. - Share and implement the framework described in “Learning in a Language other than Mother in tongue in IB Programmes” with all members of the school community. - Review of the school language Policy (see Standard B) | Completed January 2008. Semester 1 (July – Sept ) 2008 | All staff , administration and parents Administration team and a set committee of teachers and parents. | All members of the school community have a clear understanding of the IB perspective (and therefore the SC perspective) on language learning. The development of each child’s mother tongue is recognised as being crucial to cognitive development and the maintenance of cultural identity. The revised school language policy will reflect the requirements as stated by the IB and this will be the framework for daily practice in the formal and informal settings of the school. |

| Section B: Organisation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal | Strategies | Date to be achieved | Person/group responsible for achieving the goal | Evidence of achievement of, or progress towards, the goal |
| Standard B The school demonstrates ongoing commitment to, and provides support for, the programme through appropriate administrative structures and systems, staffing and resources. |  |  |  |  |
| • Involvement of all stakeholders (including the school Board) in the development and monitoring of all strategic and action planning | - Scaffold the process so that segments of strategic planning may be included in each board meeting. - Strategic Plan displayed on the school website - Development of a school parent group with the specific charter of regularly reviewing the progress of the Strategic Plan - Review the structure and agendas of Board meetings to ensure that there is a balanced time allocation to shared discussion about school educational planning. (Including agendas prepared and published by the Director for all stakeholders, prior to Board meetings). - Seek and IB Consultation Visit 3 years after the Evaluation Visit | 2009 2009 2008/09 2008/009 ongoing 2009/10 school year | Elementary/Pre-elementary Leadership team Co-ordinating P, parents School leadership Team, Board Co-ord P PYP Co-ord, IBAP office | All members of the school board are conversant with and knowledgeable about the school programmes and are therefore able to make informed shared decisions about school development based on educational requirements. Through a committee the perspectives of informed parents can be utilised to support the ongoing development of the school. An outside perspective can be provided as a framework for ongoing development. |
| • Develop systems to involve students in the implementing and monitoring of the programme. | - Engage students in a reflection of each UOI that may contribute to ongoing POI evaluation. - Use the student council XXXX to lead a forum with peers to discuss which aspects of the programme are relevant and engaging. - Further accommodate individual student inquiries in each UOI. | 2008/09 and ongoing 2009/10 (formally) | PYP Co-ords Class teachers, XXXX leaders, | Students are able to reflect beyond their work and that of their immediate peers to have a broader understanding of the programme, the rationale behind the programme and be empowered to provide thoughts and direction for the program and their own learning. |
| • Continue the policy that ensures all teachers have equal opportunities to attend regional workshops and conferences. | - Continue to select appropriate workshops and conferences that meet the specific needs of the school based on a long term PD plan. - Always advertise all conferences/workshops to the whole staff and seek ‘expressions of interest’ for attendance. - Maintain the policy of expectation of commitment to the school after participation in external training. - Explore further means of accessing online international training e.g. “Optimus online Professional Learning” to enable economical access for more staff. - Planned annual, in-school training for all staff using IB workshops or other related trainers. - Provide further professional development books, websites etc for staff. - Expand the school on line Professional Development Forum to provide a framework for in-school professional development, mentoring and sharing. | 2008/009 ongoing 2007/08 continued 2008/009 ongoing 2008/ 09 school year and ongoing if successful. Ongoing ongoing 2008 onwards | Co-ordinating P, Administration Team HRD department ITC committee, PYP Co-ord. School wide administration team, Co-ord P. PYP Co-ordinators, moderators and administration team. | An annual professional development plan is aligned with the unit and school wide strategic plan. Teachers are aware of the targeted areas for each term and can support the delivery of the program as able. Attendance at Regional Workshops/application for IB in school workshops/ other professional development linked to plan can be considered in advance. Professional development opportunities are varied but always linked to the school needs. Varied professional development opportunities can be provided for all. |
| Develop strategies that will lead to the sustainability of the school with Countrystaff. | - Maintain the policy of Country staff fulfilling all key leadership roles – e.g. Team Leaders, PYP Co-ordination Team and international teachers being seen as ‘educational mentors’. - Develop the pedagogical leadership roles of the Country principals so that they are able to be fully involved in the monitoring of the programme – i.e. delivering staff training, liaison with the IBO ( as needed), planning ongoing development, writing action plans, developing long term goals and strategies etc. - Participation in Pedagogical Leadership of the PYP Workshop. - Ongoing support to develop broad bilingual skills amongst all Country staff. - Continued staff training that empowers everyone to be engaged in curriculum development. - Support for staff to upgrade their Country teaching qualifications (current government initiative) - Review of salary status to reward exemplary, ‘international standard’ local teachers. - Instigate a scholarship programme with the Foundation for ongoing study in Masters Programmes. | 2008/09 onwards 2008/09 2009 or as available. 2008/09 and ongoing 2009/10 2009/10 2009/10 | Co-ord P Co-ord Principal Principals School wide administration HRD team Admin Team PYP Co-ord + designated staff School wide administration Director, Board, HRD management “ | Country leaders are empowered to lead the school into the future with the long term goal of reaching a fully sustainable IB World School managed and staffed by the best available educators in Indonesia. The Country leadership team has the skills, knowledge and framework to take over the shared, collaborative responsibility of leading, guiding, resourcing and monitoring all dimensions of the IBPYP. English as the language of instruction of the school and the second language of most of the teaching staff can be capably understood, and fully utilised by all teachers in every school setting. Country teachers are supported by the school and XXXXX to enhance qualifications in a manner that is commensurate with the school’s philosophical direction. |
| • Revision of the language policy using the guidelines and framework provided by the IB. | - Involve all stakeholders in the revision of the whole language policy using the IBPYP framework and with reference to “Learning in a Language Other than the Mother Tongue in IB Programmes” - Provide a questionnaire for all parents to gauge their optimum language expectations from the school. - Engage the School Board in the final ratification of the revised language policy. - Analysis of current research on what constitutes effective language learning. - Continued review of the teaching methodology employed in the planning and delivery of the Country language programme. | Semester 1 2008/09 2008/09 | School wide Administration PYP Admin Team PYP Co-ords, all staff, parents Board members Expatriate teachers Administration PYP Team, Country Committee, all home room teachers | There is a clear and updated statement on language at School which meets the current needs of the school, the criteria established by the IB and reflects what is currently considered to be ‘best practice’ in language learning. |
| • Formal inclusion of the 3-4 yr old age group KBB) in the PYP. | - A review of the POI to include the 3yr old (Playgroup) as the starting point. - Prepared and planned for the 2008/09 school year. | April 2008 (completed) | Pre-elementary Principal, Playgroup co-ordinator, PYP Co-ordinator | The school POI formally has appropriate units of inquiry included in the 3-4 yr old age setting. |

| Section C: Curriculum |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Goal | Strategies | Date to be achieved | Person/group responsible for achieving the goal | Evidence of achievement of, or progress towards, the goal |  |
| Standard C 1 A comprehensive, coherent, written curriculum, based on the requirements of the programme and developed by the school, is available to all sections of the school community. |  |  |  |  |  |
| • Review the curriculum to ensure that the students to become aware of and initiate action on global issues. | - Review the POI to ensure that issues of greater global significance are addressed through the UOI’s – esp. with thorough referral to the Transdisciplinary Theme descriptors in the vertical alignment of the POI. | 2008/09 (developing continually) | PYP Team and all teachers | The written curriculum explicitly forms the framework for the taught curriculum. The written curriculum is supported by documentation of resources, agents, and internal and external primary sources that can ensure all possible attributes of international mindedness may be explored. |  |
| • Ongoing support for the mother tongue of all students. | - Establishment of a Country culture centre within the school – to support what is currently the significant 2nd mother tongue in the school. - Review resources as needed based on enrolment trends, including Country and additional language as other groups enter the school. - Address mother tongue issues if/as the school population changes. - Broaden access to the community of parents/colleagues with different cultural background to develop resourceful partnerships.( British Council, French Cultural Centre, Japanese Cultural Centre, German Foundation) - Investigate /improve Country language reading resources to reflect a higher quality – view producing readers in the school to meet this need. - Engage (further) parents in the understanding of the importance of mother tongue as the foundation for language learning. - Formal Country language-review in the language policy – mother tongue supported in the revised Language Policy | 2009/10 2008/09 2009 and onwards 2009 onwards 2009 onwards 2008/09 and ongoing 2008 – semester 1 | Country families, translator. Community resources, parents. Country language committee, Country Principals Country Principals Country language committee, Country Principals | Country families, and/other significant groups that enter the school are empowered to join in school activities and to have a’ voice’ in the school community. Resources in the school reflect the current/transient population Primary resources in the community are noted on the school data base and can be readily accessed. All members of the school community value and support Country as the predominant mother tongue and the language of the host country. Adults in the school understand and recognise the importance of mother tongue in the whole language development of a child. |  |
| • Continued development of subject specific scope and sequence documents. | - Review –initially, the Science and Social Studies Scope and Sequences in line with the new IB documents due for release July 2008. - Incorporate the related concepts in planning by all single subject teachers. Further exploration of and consistent reference to the subject specific appendix of MPYPH. - Ensure that all scope and sequences are developed under the same framework and include: sequential skills, knowledge, conceptual understanding. - Form committees to review the existing subject specific scope and sequences of Language and Mathematics. - Develop new/ revised scope and sequences for The Arts, Visual Arts, PE and additional Language - Ensure that all teams to refer to the scope and sequence documents during planning time. - Plan the and set the order for each UOI prior to the start of the school year to enable single subject teachers to establish authentic transdisciplinary links with their scope and sequence documents. - Prioritise meeting times to enable single subject and home room teachers to collaboratively plan. - Review the possible levels of collaboration between single subject and home room teachers and devise a set of possible options as a scaffold for collaborative transdisciplinary planning across all areas. (Using a 3 level guideline from full collaboration, co-operation, links to CI and concept links). - Single subject teachers annually , nominate which units per grade level with which they will plan in a fully collaborative manner and review all other units for collaboration through the concepts, TT or strands of the unit. - Apply for an in school workshop to address curriculum development and articulation “ the “Written Curriculum and the PYP” | After July 2008 2008/09 school year 2009/10/11 With ongoing cyclic review 2008 – Language 2009 – Maths 2008-2010 2008/09 onwards April 2008 completed Reflect review 2008/009 2008/09 2008/09 onwards 2008/09 onwards Semester 2 2008/09 | PYP Team and specific committees PYP Team and separate committees Admin team, PYP Co-ord Team specific committee leaders. Committees PYP Co-ords and Team Leaders PYP Co-ords and Team Leaders PYP Co-ords and Team Leaders PYP Co-ords and Single subject teachers Co-ord Principal | All aspects of the written curriculum are developed based on current IB scope and sequence documents, and reviewed cyclically based on new documentation, changing school needs and ongoing reflection. All teachers are aware of the sequence of the UOIs. And can therefore plan ahead; involve both internal staff and external primary resource in the collaborative planning and delivery of the program. Single subject teachers can develop a year-long plan to support the levels of collaborative planning that they can provide and track the subject specific scope and sequence and integration with the POI. Teachers further enhance their curriculum development skills and are able to make the connections between the written and taught curriculum. |  |
| • Maintain and refine the system for regular review of individual units of inquiry and the programme of inquiry by all stakeholders. | - Further develop a shared understanding that will ensure central ideas, lines of inquiry and teacher questions are written conceptually to move further away from a thematic approach. - Continue to guide all planning to make the direct connection between the transdisciplinary themes, central idea, lines of inquiry and teacher questions. - Review the POI (especially Sharing the Planet and How we Express ourselves) to eliminate overlap of content within the units at each year level and to provide a balanced articulation both vertically and horizontally. - With respect to ongoing development of the nature of collaborative planning, explore the transdisciplinary nature of the units of inquiry to make authentic transdisciplinary connections as possible. - Evaluate the purpose of the weekly team leader meeting and re-direct the agenda to engage the grade leaders in the shared guardianship of the POI. - Continued annual review of the POI ensure that the Transdisciplinary Themes are consistently covered, to include issues of changing global significance, to cater for the changing needs of the school community and to accommodate the development of the PYP students as the program grows. - Expose the students to the full POI so that they can understand the significance of their learning and the holistic picture of each TT. - Form a student group within the student council to view the full POI and make recommendations as to areas of interest that may not be addressed. - Continue to share the scope of the POI with parents at training sessions, through workshops, via grade newsletters and at the commencement of each school year. | 2008/09 onwards 2008/09 onwards Completed April 2008 and to be reviewed annually 2008/09 onwards 2008/09 onwards Now and 2008/09 school year onwards Introduce 2008/09 and develop Introduce 2008/09 and develop 2008/09 | PYP co-rdinating Team “ “ “ Administration Team PYP co-rdinating Team PYP co-rdinating Team and class teachers STUCCO leaders Administration Team and PYP Co-ords | UOIs engage students in authentic inquiry, and the transdisciplinary theme and concepts play an integral role in the planning and scope of the programme. The vertical and horizontal articulation of the POI is clear and planned learning engagements build on what the students know and can do. All middle managers collaboratively review each UOI to gain further knowledge of the scope of the whole program and to provide alternative perspectives on each UOI. All stakeholders (teachers, parents and students) have an opportunity to engage in a regular reflection of the POI. |  |
| • Ongoing development to ensure that there is a balance between disciplinary and transdisciplinary planning and teaching. | - Refer to each subject scope and sequence to ensure that the knowledge skills, conceptual understandings and related concepts are included in the transdisciplinary planning when possible. - Ensue that the 5 Essential Elements are imbedded in the transdisciplinary plan for each UOI. - Document transdisciplinary skills on the planner. - Make sure the continuum of the skills is documented in all scope and sequences. - Documenting new ideas that will support and improve UOI learning engagements and share these consistently on the school professional forum. | March 2008 onwards | PYP Co-ords Team Leaders “ “ “ “ | Individual subject scope and sequence documents provide a framework for all long and short term planning both within the UOI and when covering he disciplines. |  |
| • Inclusion of Mathematics and Language within the Programme of Inquiry where possible. | - Identify the areas of Maths and Language from the scope and sequence that can be fully and partially integrated with the UOI. - Continue documenting maths integration on the program of inquiry and develop language integration on the Program of Inquiry. - Review the scope and sequence for Maths and Language. - Continue to send staff annually to regional workshops (Maths and Language focus) to support the school wide development of Maths and Language and to fulfil the role of peer mentors on their return. | At the start of each school year. 2009 sem. 2 full implementation Language 2008 Maths 2009 2008 and continuing. | Maths and Language Committees Administration Team | Maths and Language become an integral part of each UOI resulting in home room teachers approaching the written curriculum in a holistic manner with the transition between subjects becoming seamless and classroom organisation and time more efficiently utilised. |  |
| Standard C 2 The school has implemented a system through which all teachers plan and reflect in collaborative teams. |  |  |  |  |  |
| • Further develop strategies and systems to support the transdisciplinary approach by all single subject teachers. | - Continual staff training following from the strategies shared and developed during the Collaborative Planning Workshop. - Support through ongoing in school training for single subject teachers in the areas of ;Planning, Teaching, Recording, Reflection - Establish more time for single subject teachers to meet and plan with classroom teachers ( creative use of some allocated staff meetings) - Re-organise some school structures (e.g. staff meeting times once a month and after teaching hours to enable single-subject teachers to participate in the development of collaborative units. - Further support for single subject teachers to explore the impact of the concepts on transdisciplinary planning. - Place relevant/ shared resources, ideas and strategies on the school server. - Guide single subject teachers to place their reflection in the team planner (if they have collaborated within the unit). - Differentiate weekly staff training as appropriate to enable single subject teachers to explore different perspectives to home room teachers. | 2008 semester 2 and developed 2008 school year At end of the preceding school year. 2008/09 and ongoing 2008/09 and ongoing 2008/09 and ongoing Semester 1 2008 trial and reviewed | PYP Team PYP Team PYP Team Vice Principal Administration Team PYP Team PYP Team PYP Team PYP Team | A balance between the Programme of Inquiry and additional single subject teaching exists from one unit to the other BUT ...’the Programme of Inquiry remains the definitive experience from the students standpoint’ MPYPH p 14. The philosophy of collaborative planning is understood by all and strategies to support these at all levels (within and between teams) are in place and regularly reviewed. Structures that will support collaborative planning are established and reviewed regularly. Single subject teachers to review the full year UOI cycle and evaluate the transdisciplinary links |  |
| • Develop planning strategies that enable all teachers to gain an overview of each student’s whole learning experience. | - During team planning time include a ‘student welfare’ session where individual and groups of students specific needs may be shared and addressed. - Share class anecdotal records and with all contact teachers. - Create regular times where teachers can share the students’ work at each grade level. - Provide in- school assessment workshop/training for teachers who have joined the staff since the initial workshop. - Repeat a PYP in-school Assessment workshop to consolidate and further explore assessment in the planning stages a toll for gauging student understanding. | Commence 2008/009 and continuing 2009 2009 Term 2 2008 2009/10 | Special Ed Needs committee All class teachers Singe subject teachers. Admin Team PYP and Admin Teams IB office PYP Team | All teachers can fully contribute and explore the development of individual students. Assessment knowledge is further explored in the context of the current school development and with reference to global information. |  |
| • Continued focus on differentiated planning and teaching practices. | Continue to develop strategies that will empower teachers to address the needs of all students - - Cater for a range of learning needs and styles varying levels of competencies. - Include differentiated practices in the planner. - Use formative assessment to guide grouping and direction to teach. - Provide teachers with practical strategies for differentiating ability, process and product - Investigate practical in school training to help support special needs students - Purchase more resources to support teachers as they explore the range of special educational needs that exist within the school setting. - Continue to use and further explore different resources, teaching strategies, activities and assessment to cater for students with special educational needs. - Training re inclusive education and the writing of IEPs. | 2008/09 to be reviewed and developed “ “ “ “ “ 2009/10 or as trainers become apparent/ available | PYP Team, designated staff, all teachers, school counsellor, outside agents if/when relevant, parents. Admin Team SEN Committee “ | Home room and single subject teachers can identify and develop strategies to support all students to connect to the different learning environments and reach their learning potential. |  |
| • Ensure that all the essential elements (concepts, skills, knowledge, attitudes and action) are explored and addressed in the planning. | - Refer to a checklist to track the inclusion of the 5 essential elements across each grade over each year and with all disciplinary and transdisciplinary planning. - Colour code learning engagements addressed in the planner that include the essential elements (use the descriptors in assessment criteria) - Share the elements with students in the start of UOI so that they can gain a better understanding and take more responsibility for their own learning. | 2009 Trial 2008/009 2008 ongoing | PYP Team, Team Leaders “ “ | Planning is more thorough, students are provided with a framework that will guide them to authentic inquiry based learning and one that leads them to take action for individual explorations. |  |
| Standard C3 Teaching and learning at the school empowers and encourages students to become lifelong learners, to be responsible towards themselves, their learning, other people and the environment, and to take appropriate action. |  |  |  |  |  |
| • Inclusion of a greater range and balance of teaching strategies to meet the objectives of the programme. | - When planning ensure that a variety of teaching approaches are articulated in the learning engagements on the planner in Stage 4. - Revisit de Bonos’ 6 Thinking Hats, Gardener’s Multiple Intelligences and reference to Learning Styles in staff training and analyse specific examples for their implementation at different levels and across different teaching areas. - Re-addressing the purposes of grouping and regrouping for different learning engagements and strategies to achieve this. - Develop a variety of teacher resources that enable students to explore learning from diverse perspectives and cater for individual explorations e.g. worksheets, hands-on activities, on-line programs (internet), electronic teaching tools (camera, handy camera), art works, physical activities etc - Use the school online forum to share and acknowledge useful primary resources. Explore relevant resources in the community and develop an in school referencing of these. | 2008/09 onwards 2009/10 2008 – ongoing 2008/009 ongoing and developed 2008 –semester 1 | PYP Team, Team Leaders PYP and Admin Teams + specific teachers. “ Class Teachers PYP Team and in school moderators | Individual student needs are addressed within the holistic framework of each UOI. Students are provoked during the early stages of each UOI to move on and explore personal areas of inquiry that meet individual needs, abilities and learning differences. |  |
| • Incorporation of differentiated teaching practices in the delivery of the program. | - Revisit aspects of the Teaching and Learning Workshop that focussed on differentiated teaching practice and design grade level/ subject learning engagements that cater for all. - Vary the media of instruction to deepen students’ understanding. - Develop challenging inquiry activities for fast finishers (e.g. contracts, carousel learning, etc.) - Maintain small class sizes and teacher student ratio to ensure that students can be treated as individuals in the learning context. - Volunteer staff to participate in the online PD model on differentiated teaching through Optimus Learning - Explore the range of videos and support material currently available through ASCD. - In school staff workshops and scaffolding to support the teachers in their exploration of differentiated learning. - Provision of more professional readings on differentiation. | 2008/009 “ “ ongoing semester 1 2008/9 2009/10 2008 2008/09 ongoing “ | PYP co-ordinators Principals Committees Team Leaders All teachers | All teachers are more knowledgeable about differentiated teaching practices and are able to apply these to individual students ad adapt the strategies to meet individual learning environments. |  |
| • Further engagement of students as critical thinkers. | - Revisit and explore workshops on questioning techniques - In planning allocate more time for exploration through open ended questions - Incorporate strategies such as peer sharing and group exploration to ensure to inclusivity. - Ongoing training on the application of inquiry learning especially in the single subject areas. - Guide students to the development of views of their own. - Problem solving, open ended questions. - Include students’ questions in developing the planner stage 4 planner - Research and participate in global conferences, such as drug awareness, environmental issues, health, government etc. - Improve the awareness of global issues by listening/watching/reading current news and events in the daily class setting. - Encourage parents to discuss global issues with students, suggest parent news times at home with feedback to school on what has been uncovered. - Engage in on-line learning and communication with schools and primary resources around the world (internet sister schools) - Incorporate a ‘news viewing session’ in the viewing section of the literacy programme. | 2008/09 “ “ 2009/10 2008/09 ongoing “ 2009 /10 2008/09 and ongoing 2008/09 parent meetings and ongoing 2009/10 focus 2009/10 | Principals PYP co-ordinators Teaching Teams “ “ “ “ Parent committee PYP Co-ord. ITC Committee School wide leadership team. | All students are guided through appropriately scaffolded learning engagements to explore possibilities, value perspectives and develop and defend views of their own. Students engage in 21st century learning in an environment where; Questions are ENCOURAGED Thinking is EVOLVED Inquisitiveness is EMPOWERED Learning is ENHANCED Talent is ENABLED Personalities are ENRICHED |  |
| Standard C4 There is an agreed approach to assessment, and to the recording and reporting of assessment data, which reflects the practices and requirements of the programme. |  |  |  |  |  |
| • Revision of the written assessment policy. | - Involve the whole staff and use the IB guidelines and framework as a base. - When completed ensue that the Assessment Policy is available t all members of the community through the school website and parent meetings, | 2009 “ | Admin Team PYP c-ords. All teachers | The Assessment Policy clearly states; -Purposes for Assessment -Principles of assessment -Assessment practice. And... All members of the school community fully understand the complexities of authentic assessment. |  |
| • Revision of the written report to parents | - Review criteria of the written report (usually, sometimes, rarely/needs development) - Review annually the structure and content of the written reports, in consultation with a group of selected parents. - Explore the possibility of digital reporting. - Pre-elementary (3-6 yr olds) review of the written to ensure that it reflects all components of the PYP as articulated in the Early Years referring to pg 47 MPYPH and sample reports from the OCC as a framework. - Review all reports to ensure that the essential elements of the program are clearly analysed, | 2008/09 2009/ 2010 Term 1 2008/09 2010 2008 semester 1 2008 semester 1 | Administration Team, PYP Co-ordinators ITC committee Co-ordinating Principal Pre-elementary Principal Pre-elementary Principal and Team Leaders. | The written report is seen as a summative account of each student’s progress and addresses the requirements of the IB and is understood by and, meets the needs of the families at SCHOOL. The report at all levels is inclusive of increased evidence of the 5 essential elements and parents have a clear and relevant framework to view their child’s progress. |  |
| • Inclusion of all of the essential elements in assessment. | - Use of the essential elements as part of the criteria for assessment. - Provide a checklist of essential elements in the planning - Ensure that all essential elements (concepts, skills, knowledge, attitudes and action) are included in the assessment during the planning stages of the programme. | 2008/09 “ “ | Assessment policy committee PYP Co-ords PYP Co-ords Team Leaders | Teachers and students refer to the essential in teacher, peer and student assessment and reflections. Students are able to prepare their own assessment strategies based on criteria provided by teachers. |  |
| • Analysis and diverse usage of assessment data. | - Increase the reference to, and the connections between anecdotal records and future planning. Guide staff to develop a systematic means to review the records when planning for both whole class and differentiated learning. - Develop criterion based assessment strategies for effective feedback to inform and improve student learning. | 2009 (explore and structure means) 2009 semester 2 | Admin team PYP Co-ords Team Leaders Teachers Teachers | Assessment is viewed as a means to inform the evaluation and subsequent modification of teaching and learning strategies and to provide information about the individual needs of the student. Students have a clear understanding of the direction of their learning. |  |
| • Further analysis and exploration of the nature and roles of formative and summative assessment. | - Review formative assessment as it is articulated in the planner 2007, and provide further training and guidelines to support all teachers. - Clearly articulate assessment details on the planner and ensure students aware of the assessment / criteria expectations prior to embarking on learning engagements. - Revisit consistently the Wiggins ‘Understanding by Design’ model. | 2009 2009 2009 | PYP co-ords Team Leaders Teachers Administration Team | Teachers can clearly understand that in order for them to know that a child has developed, there needs to be acceptable, clearly described evidence of learning. All teachers clearly differentiate the specific purposes of formative and summative assessment: Formative; assessment for learning Summative; assessment of learning |  |
| • Further an ongoing exploration and development of student portfolios. | - Introduction of a the digital portfolio and personal web pages for all students.(Think.com) - Ensure that portfolios show evidence of the process of learning and progress over time. - review (annually) the purpose of the portfolio: clear objectives, documentation process - Give clear information to parents about the function of the portfolio. - Ensue that the portfolio selections demonstrate the process and the product and are inclusive of students self assessment, and peer/teacher/parent assessment as deemed appropriate. - Empower students to have ownership of their portfolio with access to it all times | 2009/10/11 Start of 208/09 school year Review annually 2009 208/09 ongoing | ITC Committee PYP Co-ords Admin Team Teachers “ All teachers Students | Student portfolios are diverse and reflect individual learning styles. Students have the freedom to explore different ways of developing and presenting their portfolios. |  |

| Section D: The Student |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal | Strategies | Date to be achieved | Person/group responsible for achieving the goal | Evidence of achievement of, or progress towards, the goal |
| Standard D1 Students learn to choose to act, and to reflect on their actions, so that they contribute to their own well-being and that of the community and the environment. |  |  |  |  |
| • The school needs to provide more opportunities for student action to be an integral part of the curriculum and/or an extension of the curriculum. | - Review how action can be used to demonstrate service; to fellow students and the larger community within and beyond the school. - Through the development of appropriate transdisciplinary skills empower students to connect life at school with life at home and the world therefore leading to action. - Link action specifically to inquiry “successful inquiry will lead to responsible action, initiated by the student as a result of the learning process”. MPYPH - Ascertain needs within the school and local community on an annual basis and as needs arise and develop and action plan as framework for guided action. - Develop ways in which adults can model action (e.g. continued involvement in local ‘schools to schools programme as teacher trainers) - Develop an action component as part of the leaders (STUCCO) charter. - Ensure reflection is built into all forms of action. - Continue to involve parents in the supporting and reporting on action beyond the school via daily communication books. - Support and guide students to look for areas in and outside the school that could be developed with their support and linked to the Units of Inquiry. - Linking with local schools to foster and develop student planned and sustained ‘schools to school’ support systems. | 2009/10 Ongoing development 2008/09 and ongoing 2008/09 and annually “ “ “ “ “ “ | PYP Admin team PYP Co-ordinators All teachers Parents ‘Schools to School Committee Elementary / Pre-elementary Principal STUCCO members Admin Team and parents. Home room teachers Elementary Principal ‘Schools to Schools’ committee | Teachers, students and parents understand that student initiated action is a natural process that will look different at every stage of development and is linked to the choose – act- reflect model and that the specific role of the teacher/s is to provide the opportunities that may lead to student action or if required inaction. Students are empowered to review the possibilities of taking action that may be pursued through community service and to initiate and devise programs to support this. Parents fully understand the ‘action’ component of the PYP and are able to; Recognise student initiated action Support student action Report student action beyond the school Lead their children to reflect on the action that they have hosen |
| Standard D2 In the final year of the programme, all students complete a programme-specific project that allows them to demonstrate a consolidation of their learning, in the case of PYP and MYP, and demonstrate the extension and development of their learning in the Diploma Programme. |  |  |  |  |
| • Develop assessment strategies to reflect on the exhibition. | - Develop summative assessment tools that enable students, teachers and parents to analyse the whole Exhibition process. - Build time into the post Exhibition program to ensure that adequate reflection is provided. - Develop the range of reflection tools that are suitable for each different audience – peers, teachers, mentors, parents , grade 6 students etc | 2008 onwards “ March 2008 and reviewed annually | PYP Team, grade 6 teachers and mentors. | The Exhibition is developed annually using a choose act - reflect - cycle that has input from all constituencies engaged in the exhibition. Each Exhibition builds on the experiences of the preceding year. |