| # Recommendation from the Evaluation Report | Strategies Recommended by Leadership and Teachers | Date to be achieved or progress towards assessed | Person/ Group responsible for achieving the goal | Evidence of achievement or of progress towards achievement of the goal |
| --- | --- | --- | --- | --- |
| # Standard A1: Philosophy The school continues to further promote student inquiry and the development of critical-thinking skills. Reference to research such as Bloom’s taxonomy, De Bono’s thinking tools, etc. could be used to further develop higher order thinking and the development of more in-depth questioning skills by both teachers and students. | - Hold in-school workshops on Bloom’s taxonomy, De Bono’s thinking tools and other strategies that further higher order thinking. - Hold discussions and in-school workshops on developing more in-depth questioning techniques for both teachers and students. - Show videos on inquiry from other schools - Share and discuss research articles on higher order thinking skills - Deliberately plan units with higher order thinking skills in mind. This may include Bloom’s taxonomy and DeBono’s thinking tools. | June 2008 onwards | PYP Coordinator, Teachers | - Completed in-school workshops on Bloom’s taxonomy and DeBono’s thinking tools in June 2008 - Grades 3 to 5 teachers are currently using DeBono’s thinking tools in some of their UOI and literacy activities - Grade five teachers and students are using Bloom’s taxonomy to plan for their exhibition - We will continue to have readings, workshops and discussions on inquiry and the development of critical thinking skills - We will continue to deliberately plan units with higher order thinking skills in mind |
| # Recommendation from the Evaluation Report | Strategies Recommended by Leadership and Teachers | Date to be achieved or progress towards assessed | Person/ Group responsible for achieving the goal | Evidence of achievement or of progress towards achievement of the goal |
| # Standard A2: Philosophy # An investigation of ways to utilize the cultural diversity of all students and the wider school community and to also plan support mechanisms for mother tongue language for all students. The school continues to resource and develop the productive use of the diversity of cultures, languages and perspectives that exist especially in the area of global communities to enhance learning. The IB PYP workshop on Teaching for Intercultural Understanding and Global Perspectives is recommended to develop understanding amongst all staff. | - Invite parents and other members of the community to talk about their heritage, religion and culture - Students will visit various cultural communities; the administrators and teachers will also invite people from these communities to share their culture - Students from the World Religions class will visit various places of worship: churches, a mosque, Hindu, Sikh and Buddhist temple. - For after school activities, we will create various cultural clubs and language classes (i.e. Indian, Japanese and Korean) - Continue celebrating Country and International Week - Continue incorporating global connections into our units of inquiry - Grade 5 will be going on a field trip to XXXXX as part of their inquiry into Southeast Asia. Their lines of inquiry include studying the geography of Southeast Asia, the similarities between the history, culture and people, and factors that influence their way of life. - Library will purchase books in various mother tongue languages. - Teachers will label classroom areas and common classroom materials for students who have a mother tongue language other than English. - In preschool, vocabulary for Country and other languages will be introduced through songs and storybooks. - The school will request the IBO to hold the PYP Workshop on Teaching for Intercultural Understanding and Global Perspectives in June 2009. - Continue to use the Student Language Profile completed and be able to able to give teachers the language profile of their classes. - Where mother tongue is Country, homeroom teacher will translate the instructions and help the student cope with the requirements in English, or refer out for ESL if necessary | April 2009 April 2009 April 2009 August and September2008 Nov. 2008 April 2009 April 2009 April 2009 June 2009 Nov 2008 April 2009 | Headmaster, PYP Coordinator, Teachers Headmaster, PYP Coordinator, Teachers After School activity coordinator, Parents and Headmaster, Coordinators and Teachers PYP Coordinator and Teachers PYP Coordinator and Teachers Librarian Teachers and Parents Preschool teachers Headmaster and PYP Coordinator Admissions and Teachers Teachers and ESL Teacher | - During Grade 1’s Mabuhay unit, parents were invited to talk about their childhood in various places in the Philippines. - For World Religions, a Hindu Mom shared facts about Diwali to the other World Religion students. We also celebrated the Moon Cake Festival. - During International Week, we invited an Indian musician to play his music. A puppet theater group also visited us and showed the students puppets from around the world. - Grade 2 students had pen pals from other children around the world. They inquired into the similarities and differences in their roles. - We are currently conducting Mandarin and Spanish classes for after-school activities - We will be able to diversify the classes we are offering - We celebrated Country Week in August and we included: mandatory greetings in Country in the hallways and in the classrooms, Country games, films, Country Trivia and a puppet show. Students also performed Country songs and dances during assembly. - International Week will be celebrated from Oct. 27-30. Activities include parent storytellers sharing stories from around the world and in their own mother tongue. Multi-media displays from the classes include displays of the following from around the world: store items, sounds and music, world records, museum artifacts and myths. These are all related to their current units of inquiry. - The Program of Inquiry deliberately incorporates global connections into our units of inquiry. Some of these units are: Art and Artists, Children Around the World, Citizenship, Measure It, Explorations, What Are Museums For?, Government, Mythology vs. Science and Southeast Asia - Student visit to XXXX - Books in various mother tongue languages will be available in the library - Labeled classroom areas and materials - During Country Week, the teachers sang songs and read books in Country - In-school request has been filed - Teachers have language profile of their class - Teacher instruction will be in Country for students whose mother tongue is Country and teachers work with ESL teacher when necessary |
| # It is recommended that the school investigate further access to global information and recognizes the potential for wider communication through the availability and use of appropriate information and communication, additional ICT resources and technologies. | - Provide classrooms with at least one computer - Increase number of projectors, video and camera support in the elementary school - Provide each teacher with a computer - Expand the library’s inventory to include more culturally diverse resources - Expand library staff - Provide internet access in the library - Look for schools to connect to through email, video conferencing and podcasts. This is for the purpose of sharing information and exchanging ideas. - Subscribe to educational sites such as BrainPop - Librarian and IT teacher enrich UOIs with online resources | March 2013 Ongoing March 2011 PYP Coordinator Librarian and IT Teacher | Headmaster Headmaster, Librarian June 2008 onwards Ongoing | - Classrooms will have at least one computer - There will be more IT facilities in the grade school - Each teacher will have a computer provided by the school - Expanded library resources and staff - Internet access in the library - Posted ads in the IB Community site encouraging an exchange of information and ideas with other schools - Emails and podcasts that were shared with other schools - Subscriptions to educational websites - Continued access to EBSCO and other online resources |
| # Recommendation from the Evaluation Report # Standard B: Organization | Strategies Recommended by Leadership and Teachers | Date to be achieved or progress towards assessed | Person/ Group responsible for achieving the goal | Evidence of achievement or of progress towards achievement of the goal |
| # The school continues to review needs of the programme and acquire additional print and electronic resources to support the units of inquiry and the teaching of the programme. | - Planning for the Programme of Inquiry should be done several months before the next school year so librarian and IT teacher can look for resources ahead of time - Teachers recommend resources months ahead of time - Release teacher assignments by March so if there are changes, teachers can begin observing classes and being mentored to prepare them for the next school year. - Continue to support professional development | March 2009 onwards March 2009 onwards Ongoing | PYP Coordinator, librarian, IT teacher, teachers Headmaster Headmaster and PYP Coordinator | - In March 2009, allot one of our curriculum development days to review POI and recommend resources - Continue this practice for the school years to come - Teachers will be given their assignments by March 2009 and be required to observe classes and engage in a transition process with current teachers - Continue holding in-service workshops and sending teachers to professional development opportunities |
| # The school review aspects of the language policy with regards to supporting minority mother tongue languages and develop creative ways to support additional languages within the community. | - Develop the current language policy referring to the IB publication “Guidelines for developing a school language policy 2008”. - Continue to develop the Country curriculum - It is acknowledged that the minority mother tongue language in the community is Country. We will continue to encourage the use of Country outside Country classes. For example, in UOI or special subjects, teachers can read a Country book or poem, or sing a song in Country. Teachers can also provide additional opportunities for students to practice Country in their classrooms. For example, they can write a story or poem in Country. They can also explain a situation or phenomena in Country. - Add Country signs around the school and publish our faculty and student handbooks in Country - To support additional mother tongue languages in the community, we will display classroom labels in a students’ mother tongue language. We will also provide books in the library and after school activities. - Provide opportunities for Country teachers to team teach with the homeroom teachers. | April 2009 June 2008 onwards June 2008 to onwards March 2010 June 2008 onwards June 2008 onwards | Headmaster, Pedagogical Adviser, Coordinators Country teachers Teachers Country teachers Teachers and Librarian Teachers | - A language policy that supports Country and other mother tongue languages - Currently, a draft has already been developed - Country scope and sequence documents and unit planners - The students will be able to speak Country - Students use the Country language more often across subject areas. - More Country signs around the school - Faculty and student handbooks published in Country - Classroom labels, library books and after school activities to support additional mother tongue languages - Country and homeroom teachers team teach more often |
| # The school develops policy, procedures and practices relating to teachers’ support systems for Learning Support and students with special needs. | - A team of teachers and administrators develop a policy for learning support and students with special needs - Continue providing professional development opportunities on how to handle students with special needs - Continue to develop the current procedure that involves the student study team (SST) and individualized education plan (IEP). Currently, the homeroom and special subject teachers of a special needs child meets to discuss observations and the interventions recommended by an outside specialist (usually a developmental paediatrician, psychologist or occupational therapist). The homeroom teacher then writes up an IEP which is explicitly discussed and signed by the parents before the end of the first term. At the end of the year, the SST reviews the IEP to track the progress of the special needs child. Further recommendations are provided. - Hired a special needs teacher - Continue developing procedures for provisional acceptances | March 2009 June 2008 onwards June 2008 onwards Sept 2008 January 2009 onwards | Special Education Committee Headmaster, PYP Coordinator Pedagogical Adviser, Guidance Counsellor and teachers Headmaster, Special needs teacher Headmaster and Special Needs Committee | - The creation of a special needs policy, protocols and procedures by teachers and administration - In-school workshops on special education - Teachers are sent to special education workshops - The further development of clear procedures to track a special needs child’s progress that involves all teachers and the guidance counsellor. Parents will also be more involved in this process. - Special needs teacher plays an active role in intervention of the special needs child - Clear standard procedures for students who are given provisional acceptances |
| # Recommendation from the Evaluation Report # Standard C1: Written Curriculum | Strategies Recommended by Leadership and Teachers | Date to be achieved or progress towards assessed | Person/ Group responsible for achieving the goal | Evidence of achievement or of progress towards achievement of the goal |
| Matter to be addressed: The school must complete the written curriculum including scope and sequence documents for all curriculum areas. The current written curriculum documents are in a variety of formats that have been developed at various stages of the school’s life. No consistent documentation is available that encompasses all subjects and grades throughout the PYP despite being a recommendation at authorisation. It is recommended that the school develop a format in alignment with the PYP curriculum expectations and review and develop all scope and sequence documents. There is also a need to develop coherent and consistent documents that are aligned vertically and horizontally to ensure that a balance between knowledge, skills and conceptual understanding area addressed at each grade level. | - To agree upon a scope and sequence format - To complete benchmarks for all subject areas - To cross-check benchmarks and complete scope and sequence documents - Teachers will cross-check benchmarks with the grade levels below and above them to ensure that student expectations are clear and they are prepared for the grade levels above them. - The leadership team and teachers will cross-check and ensure that there is alignment between benchmarks for PYP and MYP. - Dialogue needs to take place between grade levels (PYP and MYP) to ensure that best practices take place and transitions are seamless. - An ongoing curriculum cycle will be instated, wherein two subject areas will be reviewed per year. Scope and sequence documents for these two subject areas will then be revised as necessary. | May 2008 July 2008 October 2008 July 2009 July 2009 July 2009 onwards | PYP Coordinator and Pedagogical Adviser PYP Coordinator, Pedagogical adviser, specialists Teachers PYP and MYP Coordinators and Teachers PYP and MYP Coordinators, Pedagogical Adviser, and Teachers PYP and MYP Coordinators, Pedagogical Adviser, Teachers | - The leadership team created and agreed on a format that reflected subject-specific skills, assessed benchmarks, sample questions, sample activities and sample assessments. This was partially based on scope and sequence documents available in the OCC. - The leadership team and specialist teachers used reliable sources such as textbooks, online resources and the IBO documents to come up with benchmarks for each subject area and grade level - Completed scope and sequence documents - Teachers cross-checked benchmarks for developmental appropriateness. They will also fill out sample questions (based on key concepts), sample activities, and sample assessments based on the benchmarks and units of inquiry. (See attached for complete scope and sequence documents in all subject areas) - Complete alignment in benchmarks for all grade levels - Complete alignment in benchmarks for PYP and MYP - PYP and MYP teachers meet to talk about to ensure that there is alignment in their educational practices - Revision of scope and sequence documents for two subject-specific areas per year |
| # Recommendation from the Evaluation Report: A whole school review of the Programme of Inquiry including vertical and horizontal articulation. When reviewing the programme of inquiry, attention should be given to the inclusion of international mindedness across the programme | - To continue to review Program of Inquiry - To continue to collaborate on units of inquiry - To continue to inform all teachers and parents about our Programme of Inquiry - Teachers will continue evaluating the units of inquiry after each unit and at the end of the school year. They will reflect on the age appropriateness of the units, student engagement, availability of resources, and how the students learned the concepts, knowledge, transdisciplinary skills, subject specific skills, attitudes and learner profiles. Based on the teacher reflections, teachers and leadership will decide whether to build on a unit or change it. - Before the beginning of each year, leadership, homeroom teachers and specialists review the program of inquiry and revise based on evaluation of the previous year. | July 2008 July 2008 to ongoing July 2008 Ongoing Ongoing | PYP Coordinator, Pedagogical Adviser, Teachers PYP Coordinator, Pedagogical Adviser, Teachers PYP Coordinator PYP Coordinator, Pedagogical Adviser, Teachers PYP Coordinator, Pedagogical Adviser, Teachers | - Leadership, homeroom teachers and specialists reviewed program of inquiry from preschool to grade five to ensure that the units of inquiry build from previous knowledge learned in the lower grade levels and no duplication occurs. (See attached Program of Inquiry) - Specialists are encouraged to collaborate on at least three units of inquiry per grade level and articulate this in the programme of inquiry - Program of Inquiry is currently posted and published in the faculty room and intranet, and faculty members can share their comments any time - Homeroom and specialist teachers inform parents about the details of each unit through a unit letter. - Teachers have been regularly evaluating their units and this is reflected in their planners (see attached sample unit planners) - Revised Program of Inquiry for each school year |
| # The school reviews the current language policy with regards to support systems for the development of mother-tongue language for students whose mother tongue is not English or Country. | - Develop our current language policy - Label items in the classroom for ESL students to understand - Provide books in the library and classroom reading corner for ESL students - Invite guest speakers and parents to share stories and activities in other mother tongue languages - Offer other mother tongue languages for after school activities - Review how we provide intervention for ESL students | April 2009 June 2008 onwards | Headmaster, Pedagogical Adviser, Coordinators Teachers, Librarian, After school activities coordinator, ESL teacher | - A language policy that supports Country and other mother tongue languages - Currently, a draft has already been developed - Labelled items in the classroom with students’ mother tongue language - Books in the library representing students’ mother tongue language - Parents and resource speaker sharing their mother tongue language - After school activities offering students’ various mother tongue languages - Clear procedures for ESL students |
| # Recommendation from the Evaluation Report ## Standard C2: Planning | Strategies Recommended by Leadership and Teachers | Date to be achieved or progress towards assessed | Person/ Group responsible for achieving the goal | Evidence of achievement or of progress towards achievement of the goal |
| The identification of ways in which common planning time for single subject and homeroom teachers can be built into the programme. | - To create a time structure for collaborative planning to occur also include in the schedule time for the single subject teachers to meet as a group with the PYPC. This can be a valuable time spent in developing stand alone single - To create a schedule for collaborative planning for all teachers | July 2008 June 2008 | Headmaster PYP Coordinator and Teachers | - The school has currently allotted time on the first, third and fourth Wednesdays of each month for teaching and learning. The first Wednesday of each month is an early release day, wherein the afternoons are reserved for professional development. Collaborative planning occurs on some of these Wednesdays. - Collaborative planning occurs approximately before and after each unit, and these are plotted out in the school year’s calendar. During collaborative planning meetings, the homeroom teachers and specialists present their plans and discuss how they can work together around a central idea. - In addition to common planning time, specialists use the same planner as the homeroom teachers for units that they have agreed to collaborate on. (See attached unit planners) |
| Planning at the school is based on agreed expectations for student learning and in the context of a coherent programme. The completion of a formalized, coherent written curriculum will provide a structure for these expectations. | - Development of scope and sequence documents by coordinators and teachers. - Create a curriculum review cycle where there will be a focus on two subject areas per year. This review cycle will be done with the teachers. - Consult experts in specific subject areas to review our curriculum and give feedback - Continue to send teachers to professional development workshops that involve curriculum development | June 2008 onwards July 2009 onwards | Pedagogical Adviser, PYP Coordinator, Teachers Headmaster, PYP Coordinator, Teachers | - Completed scope and sequence documents - Completed review cycle - Subject-specific curriculum experts will review our curriculum - Teachers are sent on professional development workshops that involve curriculum development |
| Continued efforts should be made to incorporate all science learning into the units of inquiry. This is a requirement of the programme. | - Three UOIs per year focus on science, which means that there is one science unit per term - Science resource person brainstorms and thinks through activities with teachers. - Continue to review science content and standards | June 2008 onwards | PYP Coordinator, Science Resource, Teachers | - For each grade level, three science units |
| Standard C3 The school further investigate and expand upon the use of ICT as a teaching and learning tool. | - Continue to have at least one IT class per week with an IT specialist and homeroom teacher. These lessons are part of the UOIs. - Provide at least one computer per classroom - Upgrade digital cameras and other equipment - Continue to provide IT workshops for the faculty - Subscribe to educational websites | June 2008 onwards SY 2009-2010 June 2008 onwards SY 2009-2010 | IT specialist and homeroom teachers Headmaster Headmaster, PYP Coordinator IT specialist and Librarian | - IT classes held once a week with lessons that are part of the UOIs - There will be one computer per classroom and upgraded equipment - Ongoing workshops - Subscription to websites |
| Teaching at the school meets the needs of the students who are not proficient in the language(s) of instruction. | - Hired an ESL teacher; ESL teacher will collaborate with homeroom teachers on lesson plans for ESL students - Identify language proficiency of students during admission | Sept 2008 SY 2009-2010 | Headmaster Admissions | - Present employment of ESL teacher, who collaborates with homeroom teacher - Admissions provides a language profile for incoming students |
| Standard C4 The school review the assessment policy; the current policy does not clearly articulate the PYP and MYP practices occurring at the school. School wide beliefs, values and principles regarding assessment are shared; however, information regarding both programmes could be separated to avoid confusion of the reader. | - Assign an assessment committee to review report cards - Align preschool and grade school assessments where it is developmentally appropriate - Provide a system for grading in which skills are explicitly written out for major unit projects - Teachers come to an explicit agreement on how to relate and convert classroom grades to the report card - Add a midyear developmental record for preschool - Review Kinder report cards - Review policy on absences and tardiness | June 2009-March 2011 | PYP Coordinator and Teachers | - Updated assessment agreement and these include agreements on report cards, assessment tools, portfolios and conferences - Updated report cards continue to be developmentally appropriate and at the same time incorporate updated international education practices |
| Data, including evidence of development in terms of the IB learner profile, is reported to all participants in the learning process: students, parents, teachers and school administrators, and other schools at the time of transfer. | - Continue to include evidence that students are exhibiting the learner profile in report cards, portfolios, project rubrics and self assessment - Clarify what the learner profile means per grade level and include this in the report card | July 2009 | PYP Coordinator and Teachers | - Write ups, photos and sample work of how students are exhibiting the learner profile in their report cards, portfolios, rubrics and self assessment - A breakdown of learner profiles per grade level that is included in the report card |
| # Recommendation from the Evaluation Report Section D: the student | Strategies Recommended by Leadership and Teachers | Date to be achieved or progress towards assessed | Person/ Group responsible for achieving the goal | Evidence of achievement or of progress towards achievement of the goal |
| Standard D1 The school continue to expand on provision of opportunities for student action to be an integral part of the curriculum and/or an extension of the curriculum. | - Continue to give time and opportunity for students to take action inside or outside the classroom - Send teachers to the Action in the PYP workshop; those teachers will echo the workshop back to the faculty - Continue exposing students to documentaries, films and stories that include the action component - Teachers and administration reflect on how they take action - Find a bulletin board in school to display photos of students in action and/or create a School blog showing students in action - Compile a list of resources (places and people) where students can engage in possible action - During a professional development day, teachers share how their students took action so they can exchange ideas | June 2008 onwards | PYP Coordinator and Teachers | - Student action is documented in the planner - At least one teacher is sent to the Action in the PYP workshop; that teacher will echo the workshop back to the faculty - Teachers will have the opportunity to exchange and share experiences and ideas on action during professional development days |
| Standard D2 The school further develop the Exhibition process to include homeroom and single subject teachers’ collaboration with the students. | - Deliberately plan exhibition with single subject specialists - Meet periodically with specials to collaborate and exchange ideas - Continue to have a variety of single subject teachers as mentors and resource people | June 2008 onwards | Grade five teachers, specialists and PYP Coordinator | - Unit planner on Exhibition reflects the plans of all teachers involved - Both homeroom and single subject teachers will be actively involved in the Exhibition |
| There is appropriate monitoring of the exhibition, and adequate records are kept of teacher collaboration and reflection. | - For all teachers involved to reflect on the exhibition process, the actual exhibition, skills learned, topics chosen, etc. - Provide an opportunity for all teachers involved to give feedback in the form of rubrics and checklists - Compile records of exhibition sheets, materials, resources, digital information, etc. - Include final papers and other digital outputs in the library collection | November 2008 onwards | Grade five teachers and all other teachers involved | - Reflections will be documented in unit planner - Rubrics and reflections of teachers will be compiled - All other records of the exhibition will be compiled - Final papers and digital outputs will be included in the library collection |